## Project Plan
Urban Flood & Waterlogging Early Warning System — Project Plan (Pune Pilot)
Owner: Shauny — B.Tech CSE, Final Year, MIT-WPU ¦ Plan generated: 22-Aug-2026 ¦ All dates below are planned targets, adjusted as the project actually progresses
Milestone Name | Objective | Start Date | Target End Date | Demo Date | Status | Milestone Tab
M0 — Discovery & Feasibility | Define the problem, validate feasibility (technical/operational/economic/schedule/legal), and run a proof of concept on real Khadakwasla discharge data before writing any product code. | 2026-07-20 | 2026-08-21 | 2026-08-22 | Completed | M0
M1 — Data Foundation & Ward-Level Risk Engine | Stand up the data pipeline (rainfall + ward boundaries + elevation) and build a first working ward-level flood risk model. | 2026-08-24 | 2026-09-18 | 2026-09-21 | Not Started | M1
M2 — River-Corridor Model & Database Layer | Wire up PostgreSQL + PostGIS + TimescaleDB, and add the Khadakwasla discharge threshold rule as a second, connected risk signal. | 2026-09-22 | 2026-10-16 | 2026-10-19 | Not Started | M2
M3 — API Layer & Alerting | Expose the risk engine through a real API and build the alert/escalation pipeline (SMS/WhatsApp), mapped to PCMC's existing L0–L4 alert scale. | 2026-10-20 | 2026-11-13 | 2026-11-16 | Not Started | M3
M4 — Citizen & Authority Dashboard | Build the React PWA — a city-wide risk view first, with ward-level drill-down, citizen safe-route alerts, and an authority-facing EOC view. | 2026-11-17 | 2026-12-11 | 2026-12-14 | Not Started | M4
M5 — Containerization & Pilot Deployment | Containerize every service, deploy to a real k3s cluster on Oracle Cloud's free tier, and run a live end-to-end pilot test. | 2026-12-15 | 2027-01-08 | 2027-01-11 | Not Started | M5
SUMMARY
Total Milestones | 6
Milestones Completed | 1
Project Start | 2026-07-20
Planned Project End (Final Demo) | 2027-01-11
Note: M5 spans the Dec–Jan holiday period — a real schedule risk, flagged here deliberately rather than glossed over. See M5 tab.

## M0
M0 — Discovery & Feasibility (Completed)
Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependency | Delay Reason (if any) | Revised Target Date (if any)
Define & refine problem statement | Initial ward-level waterlogging framing, refined into a two-source model (rainfall + Khadakwasla river-corridor discharge). | Shauny | 2026-07-24 | Completed | 2026-07-24 | None
Technical feasibility research | Evaluated IMD API, data.gov.in, opencity.in for rainfall; bharatlas & PMC for ward boundaries; picked primary sources. | Shauny | 2026-07-29 | Completed | 2026-07-29 | Problem statement
Operational feasibility research | Researched how PMC/PCMC control rooms actually operate (multi-agency, radio/phone-first, L0–L4 alert scale) to design around real adoption behavior. | Shauny | 2026-08-01 | Completed | 2026-08-01 | None
Economic feasibility — cost model | Built single-city vs. state-level monthly cost tables (compute, DB, SMS, monitoring). | Shauny | 2026-08-04 | Completed | 2026-08-04 | None
Legal feasibility — DPDP Act 2023 review | Reviewed consent, purpose limitation, storage limitation, and breach-notification obligations relevant to citizen-submitted flood reports. | Shauny | 2026-08-06 | Completed | 2026-08-06 | None
Ward boundary data sourcing & fix | Downloaded Pune ward GeoJSON; found and fixed a real lat/lon coordinate-order bug with a custom recursive script. | Shauny | 2026-08-10 | Completed | 2026-08-12 | Technical feasibility | Source data had swapped coordinates — caught during visual verification, not a schedule delay.
Proof of Concept — Khadakwasla discharge analysis | Collected 6 real historical discharge events and cross-referenced against reported flooding; found a ~25k cusec threshold pattern. | Shauny | 2026-08-17 | Completed | 2026-08-18 | Ward boundary data
Tech stack finalization | Finalized Python/FastAPI, Postgres+PostGIS+TimescaleDB, Node/Express, Redis, React PWA, Docker+k3s, Oracle Cloud, Prometheus+Grafana. | Shauny | 2026-08-19 | Completed | 2026-08-19 | None
Repo skeleton created | Set up monorepo folders (ingestion/, risk-engine/, api/, alerting/, dashboard/) and root docker-compose.yml placeholder. | Shauny | 2026-08-20 | Completed | 2026-08-20 | Tech stack finalization
M0 Demo — College Progress Evaluation | 5-minute presentation covering problem statement, timeline, tech stack, and problem-solving/innovation for graded internal evaluation. | Shauny + Mentor | 2026-08-22 | Scheduled |  | All above M0 tasks
Tasks in this milestone: |  | 10
Completed: |  | 9
Delayed: |  | 0

## M1
M1 — Data Foundation & Ward-Level Risk Engine
Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependency | Delay Reason (if any) | Revised Target Date (if any)
Set up Python environment | Create virtual environment; install pandas, geopandas, scikit-learn, rasterio. | Shauny | 2026-08-26 | Not Started |  | None
Load & clean rainfall dataset | Merge data.gov.in (2021–25) and opencity.in (1980–2019) rainfall data into one clean dataset. | Shauny | 2026-08-29 | Not Started |  | Python environment
Load ward boundaries into geopandas | Load fixed ward GeoJSON; validate spatial joins against known Pune landmarks. | Shauny | 2026-09-01 | Not Started |  | Python environment
Source & integrate elevation data | Pull SRTM/Bhuvan elevation data for Pune; join to ward polygons. | Shauny | 2026-09-04 | Not Started |  | Ward boundaries loaded
Feature engineering | Build features: rainfall intensity, ward elevation, historical incident count per ward. | Shauny | 2026-09-08 | Not Started |  | Rainfall data, elevation data
Build baseline ward-level risk model | First working version of the rainfall/drainage risk-scoring model (rule-based or simple regression). | Shauny | 2026-09-11 | Not Started |  | Feature engineering
Backtest against known flood events | Validate model output against historically known flooded wards (sanity check, not full accuracy testing). | Shauny | 2026-09-15 | Not Started |  | Baseline risk model
Document M1 findings & prep demo | Write up what worked, what didn't, and prepare the milestone demo. | Shauny | 2026-09-17 | Not Started |  | Backtest complete
M1 Demo | Show working ward-level risk engine on real Pune data to mentor. | Shauny + Mentor | 2026-09-21 | Scheduled |  | All above M1 tasks
Tasks in this milestone: |  | 9
Completed: |  | 0
Delayed: |  | 0

## M2
M2 — River-Corridor Model & Database Layer
Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependency | Delay Reason (if any) | Revised Target Date (if any)
Set up PostgreSQL + PostGIS + TimescaleDB | Run as a Docker container locally; confirm extensions load correctly. | Shauny | 2026-09-24 | Not Started |  | M1 complete
Design database schema | Tables for wards, rainfall readings, discharge events, and risk scores. | Shauny | 2026-09-28 | Not Started |  | Database set up
Migrate data into the database | Load ward boundaries, rainfall history, and POC discharge events into the schema. | Shauny | 2026-10-01 | Not Started |  | Schema designed
Build river-corridor threshold rule | Rule-based scoring using the POC finding: ~25k+ cusecs → flag Ekta Nagar/Shivne/Bhimnagar as high-risk. | Shauny | 2026-10-05 | Not Started |  | Data migrated
Combine ward model + river-corridor rule | Merge M1's ward-level model with the discharge threshold rule into one composite city-wide + ward risk score. | Shauny | 2026-10-08 | Not Started |  | River-corridor rule, M1 risk model
Write validation tests | Test composite risk score output against the 6 known POC events — confirm it flags them correctly. | Shauny | 2026-10-12 | Not Started |  | Composite score built
Document M2 findings & prep demo | Write up the composite model's behavior and prepare the milestone demo. | Shauny | 2026-10-15 | Not Started |  | Validation tests complete
M2 Demo | Show the composite ward + river-corridor risk score, backed by the database, to mentor. | Shauny + Mentor | 2026-10-19 | Scheduled |  | All above M2 tasks
Tasks in this milestone: |  | 8
Completed: |  | 0
Delayed: |  | 0

## M3
M3 — API Layer & Alerting
Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependency | Delay Reason (if any) | Revised Target Date (if any)
Build FastAPI risk-engine service | Wrap the risk engine in a FastAPI service that reads from the database and returns scores. | Shauny | 2026-10-22 | Not Started |  | M2 complete
Build Node/Express backend | General API + auth layer, built in parallel with the FastAPI service. | Shauny | 2026-10-26 | Not Started |  | M2 complete
Connect FastAPI service to Node backend | Node backend calls the FastAPI risk service internally. | Shauny | 2026-10-29 | Not Started |  | FastAPI service, Node backend
Set up Redis queue + worker | Lightweight queue for dispatching alerts asynchronously. | Shauny | 2026-11-02 | Not Started |  | Backend connected
Integrate SMS/WhatsApp gateway (sandbox) | Connect a test-mode SMS/WhatsApp gateway API for alert delivery. | Shauny | 2026-11-05 | Not Started |  | Redis queue set up
Map alert thresholds to PCMC L0–L4 scale | Calibrate risk levels to match PCMC's existing alert protocol instead of inventing a new scale. | Shauny | 2026-11-09 | Not Started |  | SMS/WhatsApp gateway
End-to-end alert test | Simulate a high-discharge event and confirm an alert is actually sent end-to-end. | Shauny | 2026-11-12 | Not Started |  | Alert thresholds mapped
M3 Demo | Show a live simulated alert flowing from risk engine → API → queue → SMS, to mentor. | Shauny + Mentor | 2026-11-16 | Scheduled |  | All above M3 tasks
Tasks in this milestone: |  | 8
Completed: |  | 0
Delayed: |  | 0

## M4
M4 — Citizen & Authority Dashboard
Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependency | Delay Reason (if any) | Revised Target Date (if any)
Set up React + PWA project | Initialize the frontend project with PWA configuration (installable, offline-friendly). | Shauny | 2026-11-19 | Not Started |  | M3 complete
Build city-wide risk view | Primary landing view — one composite Pune-wide risk status, not a ward list first. | Shauny | 2026-11-23 | Not Started |  | React/PWA setup, M3 API
Build ward-level drill-down view | Secondary detail view for individual ward risk scores. | Shauny | 2026-11-26 | Not Started |  | City-wide view
Build citizen alert & safe-route UI | Citizen-facing alert display with suggested alternate routes. | Shauny | 2026-11-30 | Not Started |  | Ward-level view
Build authority (EOC) dashboard view | Officer-facing view highlighting high-risk wards and dispatch status. | Shauny | 2026-12-03 | Not Started |  | Ward-level view
Build citizen-reported flooding form | Simple geo-tagged “report flooding here” submission, feeding into the data confidence layer. | Shauny | 2026-12-07 | Not Started |  | Citizen alert UI
Wire up auth (citizen vs. officer roles) | Basic login/role separation using the Node/Express auth layer from M3. | Shauny | 2026-12-10 | Not Started |  | M3 backend, dashboard views
M4 Demo | Walk mentor through the full citizen + authority dashboard experience. | Shauny + Mentor | 2026-12-14 | Scheduled |  | All above M4 tasks
Tasks in this milestone: |  | 8
Completed: |  | 0
Delayed: |  | 0

## M5
M5 — Containerization & Pilot Deployment
Task Name | Task Description | Owner | Target Date | Status | Actual Completion Date | Dependency | Delay Reason (if any) | Revised Target Date (if any)
Write Dockerfiles for every service | One Dockerfile per microservice (risk engine, backend, alerting, dashboard). | Shauny | 2026-12-17 | Not Started |  | M4 complete
Docker Compose full integration test | Run every service together locally via Docker Compose; fix integration issues. | Shauny | 2026-12-21 | Not Started |  | Dockerfiles written
Provision Oracle Cloud + k3s cluster | Set up Oracle Cloud Always Free tier account and a working k3s cluster. | Shauny | 2026-12-24 | Not Started |  | None (can run in parallel) | Falls during winter break — buffer built into the following task's date.
Deploy all services to k3s | Deploy the full containerized stack to the production cluster. | Shauny | 2026-12-31 | Not Started |  | Compose test passed, k3s provisioned
Set up Prometheus + Grafana monitoring | Basic metrics dashboards for the live deployment. | Shauny | 2027-01-04 | Not Started |  | Services deployed
End-to-end live pilot test | Real data flowing in, a real simulated high-risk event, a real alert sent — on the live deployment. | Shauny | 2027-01-07 | Not Started |  | Monitoring set up
Final documentation | Write up the full pilot — architecture, decisions, known limitations, and future roadmap (Phases 2–4). | Shauny | 2027-01-08 | Not Started |  | Live pilot test passed
Final Pilot Demo | Present the complete, live, working Pune pilot to mentor — the internship's core deliverable. | Shauny + Mentor | 2027-01-11 | Scheduled |  | All above M5 tasks
Tasks in this milestone: |  | 8
Completed: |  | 0
Delayed: |  | 0